THE WENDOVER ARM TRUST

WORKING PARTY NEWS

ISSUE 28                                                                                                                        December 2001

-

-

Towards the end of November we had a rethink of our position regarding work on Stage 6, the offside wall between the stop lock and Little Tring Bridge. We had hoped to continue ready-mix pours but events put us slightly off-course.

Firstly, the original programme was to plant the first 100 metres of towpath hedge from the tip end towards Little Tring Bridge this year, the rest next year. However, an approach to the Countryside Management Services Wildwood Project for a  grant  towards the  hedge  planting

resulted in an offer of a grant of £644 for the entire 230 metres up to the bridge as they had funds in their current  financial  year  but  would have no funds for the next year. This meant that we had to divert resources to clearing out the extra length of ground and levelling off between the fence and the towpath wall during November. The hedge plants were delivered on Wednesday 28th November and are to be planted at the December 1st/2nd Working Party under the guidance of Ken Graves.

Secondly, a deep reinforced concrete raft has had to be constructed in lieu of blinding under wall section 51, the offside wall adjacent to the bridge. This is both to give a wide base to the wall and to bridge the old and new gas main trenches under this section. Sheet steel piling (kindly lent to us by British Waterways) had to be placed in the sand infill used by the contractors as backfill to the abutment of the new bridge to allow construction of the raft.  Fortunately the raft was complete before the torrential rain in November turned the sand almost liquid and pushed the piles forward. The piles were strutted and are clear of the new wall formwork. Nevertheless the work on the raft took time added to which we lost one and a half days due to torrential rain; the plus side was that our site hut had a complete tidy up, including a load to the local tip, while we were rained-off!

At a special work party last week the excavation of the old offside wall right up to the lock was completed and has exposed the ‘S’ bend at the end of the lock with bull nosed blue bricks on top. Demolition of the old concrete offside wall is proceeding but it is a long and laborious task using an hydraulic breaker but we are benefiting from a load of hardcore to form the temporary road for the ready-mix lorries. We are now far enough advanced with blinding to recommence pouring base and wall sections, commencing with base 52 on Saturday 1st December 2001 and wall 50 on Wednesday 12th December 2001. It has not been easy setting out curves for the wall along this section and leave room for the footpath at the bottom of the steep bank. The old wall did not allow for the extra width of a footpath now required by modern standards.

In order to get ready-mix lorries close enough to the walls, we are having to lower the old canal bed leading up to the lock by two or three feet before laying the hardcore road. It was hoped to continue this at the December 1st/2nd 2001 work party but the present rains have made our temporary roads very wet and, as we know from experience, it only churns them up to continually run dumpers over them. Instead, at this work party, it is intended to place the sheet steel piles in the end of the lock to complete the bund (dam) to accommodate the footpath/towpath walkers clear of the work required to connect the new walls to the end of the lock.

Finally I must express my gratitude to all of you who have worked so hard throughout the year despite the bad weather conditions and especially those who have worked extra days to try and catch up with our programme. You will see on page 3 that I have re-programmed our work ahead to fit in with the future programme that I wrote about in the October Newsletter. I have also included the current budget figures and costs to date so that you can get some idea of what it costs for plant hire and materials, as well as overheads such as insurance,  plant and equipment, this newsletter, running the VW Transporter, environmental impact reports, WRG accommodation and so on.

Web Site

At the November meeting of the Trust Council the question of the Trust Web Site was debated and it was agreed to have a new site covering every aspect of the Trust’s activities, Torkel Larsen to run the main site with a linked Festival site run by another Trust member, Peter Andrews. This is likely to operate early in the New Year and will be accessible under the present working party web site address until new web site addresses are published in this Newsletter and the Trust’s Newsletter. I must express my appreciation to Trust Member Richard Emsley who has looked after our Web Site from the beginning of 1999 until now. One reason for the change is that we now have digital cameras recording events at work parties and Richard is too far away from us to keep the web site up to date as a result of this advance in technology.

The address of our working party web site is

nsa.dircon.co.uk/wendover.htm

General Notes

Hard hats for use at all times and high visibility jackets to be worn on sites with mobile plant in use are kept in the store at Tringford and must be drawn/returned there. One first aid kit is kept in the store; another is kept in the VW transporter for use on site. Also available in the transporter are ear defenders and goggles that must be worn when using strimmers, angle grinders, concrete breakers  and the like.

My mobile phone number at working parties is 07850-170858. It is not always left on continuously but has a message facility that I check from time to time.

We normally work from 10am to 5pm (or dark if earlier!) other than times when we are hiring plant or taking delivery of ready-mix concrete early in the morning when some volunteers are asked to start at 9am.  There are breaks for morning coffee/tea, packed lunch and afternoon tea/coffee. We take our own food and drinks.  However, do not feel bound by these times, as half a day is better than no help at all.  We have an electric kettle and tea urn at the hut; also there is an outside tap for drinking water.

Roger Leishman, Restoration Director (Tel:01442 874536, e-mail  rleishman@ukgateway.net)

DATES FOR WORKING PARTIES (OTHERS MAY BE ARRANGED AT SHORT NOTICE)

| DATE | WORKING AT | WORK TO BE DONE |
| --- | --- | --- |
| Wednesday 12th December and Thursday 13th December 2001 | Little Tring | With Pete Bowers, weather permitting, pour last winding hole wall (50) and move formwork to offside wall (51) at bridge (Stage 5). Alternative is scrub bashing at Whitehouses. |
| Saturday 5th January and Sunday 6th January 2002 | Little Tring | Weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Thursday 10th January 2002 | Little Tring | With Pete Bowers. If a second day can be arranged, and weather permitting, pour base/wall sections and move formwork. Alternative is scrub bashing at Whitehouses. |
| Thursday 17th January and Friday 18th January 2002 | Little Tring | With Pete Bowers, weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Saturday 2nd February and Sunday 3rd February 2002 | Little Tring | Weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Thursday 14th and Friday 15th February 2002 | Little Tring | With Pete Bowers, weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Saturday 23rd February and Sunday 24th February 2002 | Little Tring | BITM weekend. Weather permitting, pour base/wall sections and move formwork. Blinding concrete. Cut old tip towpath hedge. |
| Thursday 28th February and Friday 1st March 2002 | Little Tring | With Pete Bowers, weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Saturday 2nd March and Sunday 3rd March 2002 | Little Tring | Weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Thursday 14th March and Friday 15th March 2002 | Little Tring | With Pete Bowers, weather permitting, pour base/wall sections and move formwork. Alternative is scrub bashing at Whitehouses. |

Numbering of wall sections, with position as at 1st December 2001, is as follows:

| From section | To section | Stage | Current position |
| --- | --- | --- | --- |
| 1 | 24 | 1 Old tip to bridge, towpath side | Complete |
| 25 | 41 | 2 Bridge to farm crossing, offside | Bases 25 & 26, wall 25 completed |
| 42 | 50 | 2 Old tip to winding hole, offside | All bases and walls 42 to 49 completed |
| 51 | 59 | 6 Bridge to stop lock, offside | Base 51 complete. |
| 60 | 68 | 5 Stop lock to bridge, towpath side | Not yet started |
| 69 | 73 | 4 Bridge to Stage 1 wall, towpath side | Not yet started |

SCHEDULE OF RESTORATION WORK BY LENGTHS

| Phase | Location | Mileage | Length | Length Metresm | Description | Budget | % complete | Cost to date or final cost | Programme or Actual Dates if complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Bulbourne Jc. to Stop Lock | 0m 0y to 1m 440y | 1m 440y | 2031 | Present length open to Navigation (limited turning) |  | N/A |  |  |
| I | Stop Lock to Little Tring Br | 1m 440y to 1m 532y | 92y | 85 | Stage 3 – bund in stop lock Stage 5 – 75m towpath wall Stage 6 – 75m footpath wall Stage 7 - 800sq.m lining | 500 7,843 7,843 8.000 | 75 0 15 0 | 150 202 3,404 | Complete by 2001 May 2002 – Dec 2002 Oct 2001 - May 2002 Oct 2002 – May 2003 |
| I | Little Tring Bridge (No.3) | 1m 532y |  |  | Bridge rebuilding Stage 4 – 40m towpath wall | 221,000 4,928 | 99 0 | 217,000 112 | Complete bar steps Jan 2003 – Jun 2003 |
| I | Bridge No.3 to end past the Winding hole | 1m 532y to 1m 803y | 271y | 250 | Fencing off site Stage 1 – 215m towpath wall Stage 2 – 80 m wall at winding hole 153 m offside wall 65m reed bed Stage 7 – 4,200sq.m lining Stage 8 – bund at end of Phase I | 500 20,000 ) 25,630 ) ) ) 56,000 500 | 98 90 5 0 0 0 | 236 19,210 ) 13,192 ) ) ) | Complete bar towpath and hedge planting. Jan – Dec 2001 Apr 2001 – Dec 2003 Jan 2004 – May 2004 Jun 2003 – May 2004 May 2004 |
| I |  |  |  |  | Temporary access roadways | 2,500 | 90 | 2,773 | Ongoing to May 2004 |
| I |  |  |  |  | Overhead costs for Phase I | 17,000 |  | 13,315 |  |
| II | End of Phase I to HCC track entrance | 1m 803 to 1m 1097 | 294y | 271 | Length of canal with ash infill used for hardcore etc. storage Bottle Club recovery | -1,492 | 100 | -1,492 | Requires annual strimming of weeds. |
| II | Track entrance to Whitehouses footpath crossing (was Br.No.4) | 1m 1097 to 1m 1720 | 623y | 575 | Length cleared during 1999 and 2000 with temporary road for access. Banks to be levelled off . Provision of temporary roadway. Ongoing maintenance Relining NYE | 1,000 500 | 100 100 |  | Free use of plant from Priory Constr. - do - When resources are available |
| II | Whitehouses Crossing to Herts/Bucks CC’s boundary | 2m 1720y to 2m 759y | 799y | 738 | Length requiring clearance from scratch . Banks to be levelled off. Provision of temporary roadway. Ongoing maintenance Relining NYE | 3,000 500 | 11 |  | When resources are available |
| II | CC’s boundary to manhole east of Drayton 5) | 2m 759y to 2m 1314y | 555y | 512 | Length already cleared. Ongoing maintenance Relining NYE | 500 | N/A | -86 | Requires annual strimming of weeds. 2001 strimming prevented by floods and foot & mouth! |
| II | Manhole to end of Aston Clinton by-pass diversion | 2m 1314y to 2m 1530y | 216y | 200 | Length already cleared, BW are relining this length in conjunction with by-pass diversion. | 0 |  |  | 2001-2003? |
| II | Aston Clinton By-pass diversion | 2m 1530y to 3m 312y | 542y | 500 | Diversion for Aston Clinton by-pass by Highway Authority | 0 |  |  | 2002 |
| II | New winding hole | 3m 312y |  |  | To be built by Highway Authority but extra cost over a channel to be paid for by the Trust | 10,000 |  |  | 2002 |
| III | New winding hole to end of Arm at Wendover | 3m 312y to 6m 1352y | 3m 1040y | 5834 | Length under water but not to navigable depth. Bridge obstructions at Aston Clinton and Halton. | NYE |  |  |  |
|  |  |  |  |  | Totals | 386,252 |  | 268,016 |  |

YE = Not yet estimated

DATES FOR WORKING PARTIES (OTHERS MAY BE ARRANGED AT SHORT NOTICE)

| DATE | WORKING AT | WORK TO BE DONE |
| --- | --- | --- |
| Wednesday 12th December and Thursday 13th December 2001 | Little Tring | With Pete Bowers, weather permitting, pour last winding hole wall (50) and move formwork to offside wall (51) at bridge (Stage 5). Alternative is scrub bashing at Whitehouses. |
| Saturday 5th January and Sunday 6th January 2002 | Little Tring | Weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Thursday 10th January 2002 | Little Tring | With Pete Bowers. If a second day can be arranged, and weather permitting, pour base/wall sections and move formwork. Alternative is scrub bashing at Whitehouses. |
| Thursday 17th January and Friday 18th January 2002 | Little Tring | With Pete Bowers, weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Saturday 2nd February and Sunday 3rd February 2002 | Little Tring | Weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Thursday 14th and Friday 15th February 2002 | Little Tring | With Pete Bowers, weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Saturday 23rd February and Sunday 24th February 2002 | Little Tring | BITM weekend. Weather permitting, pour base/wall sections and move formwork. Blinding concrete. Cut old tip towpath hedge. |
| Thursday 28th February and Friday 1st March 2002 | Little Tring | With Pete Bowers, weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Saturday 2nd March and Sunday 3rd March 2002 | Little Tring | Weather permitting, pour base/wall sections and move formwork. Blinding concrete. Alternative is scrub bashing at Whitehouses. |
| Thursday 14th March and Friday 15th March 2002 | Little Tring | With Pete Bowers, weather permitting, pour base/wall sections and move formwork. Alternative is scrub bashing at Whitehouses. |

Numbering of wall sections, with position as at 1st December 2001, is as follows:

| From section | To section | Stage | Current position |
| --- | --- | --- | --- |
| 1 | 24 | 1 Old tip to bridge, towpath side | Complete |
| 25 | 41 | 2 Bridge to farm crossing, offside | Bases 25 & 26, wall 25 completed |
| 42 | 50 | 2 Old tip to winding hole, offside | All bases and walls 42 to 49 completed |
| 51 | 59 | 6 Bridge to stop lock, offside | Base 51 complete. |
| 60 | 68 | 5 Stop lock to bridge, towpath side | Not yet started |
| 69 | 73 | 4 Bridge to Stage 1 wall, towpath side | Not yet started |