THE WENDOVER ARM TRUST

WORKING PARTY NEWS

ISSUE 52                                                                                                                                   December 2005

-

-

As another year approaches we have been taking stock of Phase II. As expected, the weather conditions have called a halt to profiling and lining at Drayton Beauchamp except for using surplus ready-mix concrete from the footbridges to continue capping over the pipe trench where the reinforcement and formwork is already prepared for pouring.

At the footbridge sites, we have been renewing our acquaintance with both base and wall formwork that has been stored in the hut since our last pour in November 2003 – two years ago!

A Merry Christmas and a

Happy New Year to you all

Ken Graves has refurbished the timber shuttering that was showing signs of old age after 75 pours in Phase I using shutter ply left over from the by-pass works donated to us by Balfour Beatty. He has also made some improvements as a result of our experience during Phase I. Some of you will remember that several modifications were also made during Phase I, again the result of experience.  Eddy Evans has reconditioned all the fastenings and fittings for the steel formwork for the wall upstand as well as the two poker vibrator units. Many thanks, Eddy and Ken.

A change in the method of wall construction has been made necessary.  When our ‘Purchasing Manager’, Ron Pittaway was ordering all the materials necessary for more wall construction, he was unable to obtain the wide dovetail water bar that we used at the rear of the wall joints. There was none available in the UK and even if obtainable from mainland Europe, there was no firm delivery date.  We therefore decided to use the 25mm x 20mm Bentonite strip (that we use for the joint between the wall and base) in the vertical wall joints so Ken Graves made the timber formers fixed to the stop end boards to form the necessary groove.

Footbridges 4 and 4A

As reported in the last newsletter, the blinding for the narrows walls for both footbridges has been completed and now the base of both walls for bridge 4 have been cast and at the January work party it is hoped to cast both walls of bridge 4 and the first base of bridge 4A. The intention is to finish the necessary work needed to install the two timber footbridges by the end of April.

We have also started to clear the area of trees required to lay a footpath up to the offside steps of bridge 4.

The two footbridges have been manufactured by Martin Childs Ltd. at their works in Suffolk and have been inspected by Ron Pittaway, Ray Orth and myself to our satisfaction.  To avoid storing the bridges in the open, the firm are storing them in their premises until we call for delivery in April/May when the foundations are ready.

The intention is to construct the main framework of the two footbridges over the first May Bank Holiday weekend but it must be stressed that, due to the Health & Safety aspect, this is a task that will be very carefully planned and limited to a small team of volunteers who have been very carefully briefed on the overall operation.

A meeting has been held with Herts County Council and Dacorum Borough Council representatives to agree the diversions that are required for the two footpaths crossing at the bridges. The normal cost of diversion orders is in the order of £3,000 to £5,000 pounds per diversion, i.e. up to £10,000! Fortunately, although HCC have declined to give us a grant towards footbridge 4A, they are waiving the diversion costs for the two bridges.

The cost of the two footbridges and supporting narrows is estimated to be around £26,000 (excluding any diversion order costs) and it is very gratifying to report that we have already received over £20,000 in grants and donations specifically for these bridges.

The former Herts County Council tip at bridge 4A

The footpath that crosses the canal at footbridge 4A approaches from the west alongside an old rubbish tip that then extends along the offside of the canal for some 150 metres towards Little Tring in the form of a high, steep bank. There is no BW boundary fence on the offside although it is known from old plans that the footpath was on BW land at the top of the canal bank when the canal was in water. The land on the offside is owned by HCC and I have had a meeting with their Land Agent, John Hunt, and their tenant farmer, Keith Slade, and agreed with them that the Trust will consolidate the bottom of the tip bank by tipping at least one metre of spoil right up to the face of the tip. The tip is not moving towards the canal at present, other than loose debris falling down the slope, but the whole tip area is sinking due to decomposition of rubbish tipped in the 1950/60s. When all is complete it will be necessary to erect a post and wire fence on the boundary.

This will mean clearing the area of (mainly) old elder trees, perhaps a job for KESCRG who are joining us over the first May Holiday weekend.

Phase II at Drayton Beauchamp

As already reported, this work is in abeyance until the weather changes for the better. A supply of concrete blocks, solid and hollow have been delivered for when we are ready to start trial lining.

Little Tring

Ken Graves and his team successfully planted the new hedge across the tip in the triangle at Little Tring at the December work party. A farm gate still has to be purchased and installed to give access to the tip for our plant.

There is still a job for the ladies in March when we intend to ‘nip the thistles in the bud’ over the area behind the winding hole in front of the new hedge.

Web Site

The address of the Trust Restoration web site managed by Oliver Revel (that is linked to the main Trust site) is:

http://wendovercanal.org.uk/

E-mail

I have only received one request so far for this newsletter to be sent to readers by e-mail; this does save the Trust postage costs.  If you give me a request for e-mail transmission I will do so but please let me know if the attachment arrives or not. If it does not arrive I will then make a second attempt but if this fails I will send the newsletter by post.

Wendover Trust Mugs

If you did not have the chance to buy mugs at the Festival, Brian Ing, Ray Orth or myself have them for sale. They are bone china, £6 each, two for £11.50 or four for £22. If you did not see them, they commemorate the opening of Phase I with a view through Little Tring Bridge on both sides with ‘Wendover Arm Trust 2005’ underneath.

Insurance

As some of us are not as young as we were (!), I took up the matter of age against insurance with the IWA who insure us and confirmed that there is the well known lower age limit of sixteen but there is no upper age limit, but it is incumbent on anyone, regardless of age, to inform the Trust in writing if they suffer from any medical condition that could in any way affect their ability to carry out their work as a Trust Work Party Volunteer.

User Manuals will be updated to include this requirement so that, when you sign that you have read your manual, or amendments to it, you will acknowledge your responsibility in this matter. Any incident arising from an undeclared medical condition will not be covered by the Trust’s insurance.

General Notes.

All volunteers receive and sign for the Trust’s Restoration Manual that includes full Health and Safety requirements for the restoration works. The Manual is the property of the Trust; if you leave the working parties for any reason, please return the Manual to either Ray Orth or myself.

David Barratt is our qualified First-Aider and, even if he is not on site, lives nearby and can be contacted on 07973 411176 if he is at home.

Hard hats for use at all times and high visibility jackets to be worn on sites with mobile plant in use are kept in the store at Tringford and must be drawn/returned there. One first aid kit is kept in the store; another is kept in the VW transporter for use on site. Also available in the transporter are ear defenders and goggles that must be worn when using strimmers, angle grinders, concrete breakers and the like.

We normally work from 9am to 5pm (or dark if earlier!) when we are hiring plant or taking delivery of ready-mix concrete early in the morning.  There are breaks for morning coffee/tea, packed lunch and afternoon tea/coffee. We take our own food and drinks.  However, do not feel bound by these times, as half a day is better than no help at all.

DATES FOR WORKING PARTIES

| DATE | WORKING AT | WORK TO BE DONE |
| --- | --- | --- |
| Friday 6th January 2006 | Bridge 4 Bridge 4A | Erect Acrow props and pour first bridge 4 wall. Strip second base formwork and move to bridge 4A. Erect fencing around bridge 4A site. |
| Saturday 7th January 2006 | Bridge 4 Bridge 4A | Strip wall formwork and move to second wall of bridge 4. Erect formwork for first base of bridge 4A |
| Sunday 8th January 2006 | Bridge 4 Bridge 4A | Strip wall formwork and move to second wall of bridge 4. Erect formwork for first base of bridge 4A |
| Monday 9th January 2006 | Bridge 4 Bridge 4A | Pour bridge 4 second wall. Pour bridge 4A first base. Surplus ready-mix concrete to be used for pipe capping. |
| Tuesday 24th January 2006 | Bridge 4A | Strip first base formwork and erect for second base |
| Wednesday 25th January 2006 | Bridge 4A | Strip first base formwork and erect for second base |
| Friday 3rd February 2006 | Bridge 4 Bridge 4A | Pour bridge 4A second base. Surplus ready-mix to be used for pipe capping. Strip second bridge 4 wall formwork and move to bridge 4A. |
| Saturday 4th February 2006 | Bridge 4 Bridge 4A | Prepare rough shuttering for bridge 4 foundations. Erect formwork for first wall of bridge 4A Strip formwork from bridge 4A second base and move to bridge 4. |
| Sunday 5th February 2006 | Bridge 4 Bridge 4A | Prepare formwork for bridge 4 mass concrete fill under foundations. Erect formwork for first wall of bridge 4A |
| Monday 6th February 2006 | Bridge 4 Bridge 4A | Pour first wall of bridge 4A. Pour mass concrete fill under foundations for bridge 4. |
| Thursday 23rd February 2006 | Bridge 4 Bridge 4A | Strip formwork from mass concrete fill at bridge 4. Prepare formwork for bridge 4A mass concrete fill under foundations on one side only. |
| Friday 24th February 2006 | Bridge 4 Bridge 4A | Strip formwork from mass concrete fill at bridge 4. Prepare formwork for bridge 4A mass concrete fill under foundations on one side only. |
| Friday 3rd March 2006 | Bridge 4 Bridge 4A | Strip wall formwork and move to second wall of bridge 4A. Backfill bridge 4 walls and excavate for mooring wall on offside |
| Saturday 4th March 2006 | Bridge 4 Bridge 4A | Strip wall formwork and move to second wall of bridge 4A. Backfill bridge 4 walls and excavate for mooring wall on offside. Prepare for blinding concrete on offside wall. Prepare formwork for foundations of bridge 4. |
| Sunday 5th March 2006 | Bridge 4 Bridge 4A | Strip wall formwork and move to second wall of bridge 4A. Backfill bridge 4 walls and excavate for mooring wall on offside Prepare formwork for foundations of bridge 4. |
| Monday 6th March 2006 | Bridge 4 Bridge 4A | Pour second wall of bridge 4A Pour mass concrete fill on one side of bridge 4A. Pour foundations for bridge 4. |
| Friday 31st March to Monday 3rd April 2006 | Bridge 4 Bridge 4A | Continue work on bridges 4 and 4A and restart work at Drayton Beauchamp if weather permits |
| Friday 28th April to Monday 1st May 2006 | Bridge 4 Bridge 4A | KESCRG are joining us for this weekend and hopefully we will be erecting the two footbridges and clearing the area at bridge 4A for tipping at the foot of the old Council Tip. Note that this replaces the first weekend in May both to suit KESCRG and to leave a reasonable gap before the Festival. |
| Thursday 25th May to Tuesday 30th May 2006 | Little Tring | Tring/Wendover Festival |
|  |  | Note that, as usual, there is no June work party as it is too near the Festival. |
| Saturday 1st July to Sunday 2nd July 2006 |  | Will anyone volunteer to be in charge this weekend – it is the boating season! |
| Saturday 8th August to Sunday 13th August 2006 | Drayton Beauchamp | PLEASE BOOK THIS IN YOUR DIARY FOR ANY DAYS YOU CAN MANAGE SO THAT WE CAN HAVE A CONCERTED EFFORT AT LINING AT DRAYTON BEAUCHAMP. |

Roger Leishman, Restoration Director.  7 Hall Park, Berkhamsted, Herts HP4 2NU.

(Tel:01442 874536, e-mail rleishman@ukgateway.net)

WORK PARTY VOLUNTEER SCHEDULE TO MAY 2006

| Date | Location |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 2006 |  |  |  |  |  |
| Fri 6 Jan | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(base) |  |  |  |
| Sat 7 Jan | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(base) |  |  |  |
| Sun 8 Jan | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(base) |  |  |  |
| Mon 9 Jan | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(base) |  |  |  |
| Tue 24 Jan | Bridge 4A | P Bowers(base) |  |  |  |
| Wed 25 Jan | Bridge 4A | P Bowers(base) |  |  |  |
| Fri 3 Feb | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(base) |  |  |  |
| Sat 4 Feb | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(founds) |  |  |  |
| Sun 5 Feb | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(founds) |  |  |  |
| Mon 6 Feb | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(founds) |  |  |  |
| Thu 23 Feb | Bridge 4 Bridge 4A | P Bowers(founds) |  |  |  |
| Fri 24 Feb | Bridge 4 Bridge 4A | P Bowers(founds) |  |  |  |
| Fri 3 Mar | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(founds) |  |  |  |
| Sat 4 Mar | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(founds) |  |  |  |
| Sun 5 Mar | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(founds) |  |  |  |
| Mon 6 Mar | Bridge 4 Bridge 4A | R Orth(wall) R Leishman(founds) |  |  |  |
| Fri 31 Mar | Bridge 4 Bridge 4A | R Orth |  |  |  |
| Sat 1 Apr | Bridge 4 Bridge 4A | R Orth |  |  |  |
| Sun 2 Apr | Bridge 4 Bridge 4A | R Orth |  |  |  |
| Mon 3 Apr | Bridge 4 Bridge 4A | R Orth |  |  |  |
| Fri 28 Apr | Bridge 4 Bridge 4A | R Leishman |  |  |  |
| Sat 29 Apr | Bridge 4 Bridge 4A | R Leishman |  |  |  |
| Sun 30 Apr | Bridge 4 Bridge 4A | R Leishman |  |  |  |
| Mon 1 May | Bridge 4 Bridge 4A | R Leishman |  |  |  |

(……….) Indicates provisional

The name of the person in charge on a particular day/site is printed in italics.

P Bowers         01255 514540 or 07880 744730            E Evans     01628 526237 or 01628 526898

R Pittaway     01296 630968 or 07946 484156            K Graves   01494 563813